## Bug Report
Website Bug Report
Bug ID | Date Reported | Reporter | Page / URL | Area / Feature | Bug Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Browser / Device | Evidence / Screenshot Link
BUG-001 | 2026-08-09 | Your Name | https://example.com/checkout | Checkout | Checkout button does not respond | Clicking the checkout button does not continue to the payment step. | 1. Open cart 2. Add an item 3. Click Checkout | User should proceed to the payment page. | Nothing happens after clicking Checkout. | High | High | Open | Chrome 127 / Windows 11
BUG-002 | 2026-08-10 | Zonda Attila | https://cm.getmytestdomain.com/ | Front page /Subscriptions | Register now Button missing from "FIRST TIME PACKAGE" | No interractable button on the First time package "register now" | 1.Open Link 2. Scroll down to Subscriptions area | User should have a button inside the first package card which says REGISTER NOW | Missing Register NOW button | Low | Low | Open | Chrome 127 / Windows 11 | https://imgur.com/a/mqyg6eu
BUG-003 | 2026-08-11 | Zonda Attila | https://cm.getmytestdomain.com/ | Front page /Subscriptions | Missing Shrink Animation Register now button | Starter package card has a button REGISTER NOW which does not follow the same animation like the other two cards does | 1.Open Link 2. Scroll down to Subscriptions area 3.Hower with mouse cursor over the REGISTER NOW button | The user should have the experience of the shrink animation like on the rest of the Register now buttons | Nothing happens if you hover over the REGISTER NOW button inside STARTER PAKCAGE CARD | Low | Low | Open | Chrome 127 / Windows 11
BUG-004 | 2026-08-12 | Zonda Attila | https://cm.getmytestdomain.com/ | Front page /Subscriptions | Text and background almos has same colors | FIRST TIME PACKAGE , POWER PACKAGE, MASTER PAKCAGE: text color style="color: rgb(227, 226, 226);" background: rgb(255, 255, 255) The two colors almost identical | 1.Open Link 2. Scroll down to Subscriptions area 3.Check the text and backgrond color inside Dev tool | The user should have a clean and easily readable text | The text is blurry not visible enough hard to distinguish for the human eye | Low | Medium | Open | Chrome 127 / Windows 11 | https://imgur.com/6BqxBEo
BUG-005 | 2026-08-13 | Zonda Attila | https://cm.getmytestdomain.com/ | Front page / Video Courses | WE RECOMMEND TEXT POSITION | The text WE RECOMMEND is slightly inside the video Banner | 1.Open Link 2. Scroll down to Video Courses 3. Check the text "WE RECOMMEND" | The user should have a clean and easily readable text | The text is cut halfway through horizontally | Low | Low | Open | Chrome 127 / Windows 11 | https://imgur.com/zzDCMDS
BUG-006 | 2026-08-14 | Zonda Attila | https://cm.getmytestdomain.com/ | Front page / Video Courses | VIDEO BANNER MISSING THUMBNAILS AND BORDER | Video banner has missing Thumbnails and borders everything falls into one shape | 1.Open Link 2. Scroll down to Video Courses 3. Check the video banner | The user should have a clean experience accesing the videos 1 by 1 and a thumbnail preview | The videos are hard to be distinguished and dificult interacting with them | Low | Medium | Open | Chrome 127 / Windows 11 | https://imgur.com/hjHIK93
BUG-007 | 2026-08-15 | Zonda Attila | https://cm.getmytestdomain.com/ | Front Page / Articles | 404 ¦Not Found | Interecting with each card inside Article sections pops an error 404 | 1.Open Link 2. Scroll down Articles 3. Interact with each card | The user should be redirected based on their choice to the right article | clicking on any of the articles user ends up with an error "404 ¦Not Found" | Medium | High | Open | Chrome 127 / Windows 11 | https://imgur.com/Q0sjfdA
BUG-008 | 2026-08-16 | Zonda Attila | https://cm.getmytestdomain.com/ | Front Page / Articles | Wrong article redirect | Interacting with the article "TOP 10 BEGINNER TIPS FOR THE BEST RESULTS" Redirects the user to the Login page | 1.Open Link 2. Scroll down Articles 3. Interact with article TOP 10 BEGINNER TIPS FOR THE BEST RESULTS | The user should be redirected to the right article | User ends up on the login page | Medium | High | Open | Chrome 127 / Windows 11 | https://imgur.com/2FOy18W
BUG-009 | 2026-08-17 | Zonda Attila | https://cm.getmytestdomain.com/ | SIGN UP / Personal information | Email input field restricted to numeric values only | Email field incorrectly accepts only integer/numeric input instead of text/alphanumeric format therefore blocks the registration process | 1.Open Link 2.Click on Sign Up 3. Under Personal Information click Email field and start typing text | The user should be allowed to type in their email address | The Email field accepts only numeric/integer characters. Users are unable to enter letters or a valid email address format such as name@example.com | Critical | Urgent | Open | Chrome 127 / Windows 11
BUG-010 | 2026-08-18 | Zonda Attila | https://cm.getmytestdomain.com/ | SIGN UP / Personal information | Re-enter password missing | There is no field upon registration which ask the user to repeat the password | 1.Open Link 2.Click on Sign Up 3. Under Personal Information missing field "repeat password" | The user should have a field to repeat the password upon registration because it reduces the chance of misspelling | The User might enter the password worng or with extra characters and the sistem gives no warning of the missmatch | High | High | Open | Chrome 127 / Windows 11
BUG-011 | 2026-08-19 | Zonda Attila | https://cm.getmytestdomain.com/ | SIGN UP / Payment Methods | Cardholder Name field incorrectly accepts numeric/integer input | Cardholder Name field accepts numeric characters instead of restricting input to valid name text. | 1.Open Link 2.Click on Sign Up 3.Under payment methods interact with card holder name field input int | The user should not be allowed to type in numeric values | The Cardholder Name field accepts numeric values, allowing entries such as 12345 | Low | Low | Open | Chrome 127 / Windows 11
BUG-012 | 2026-08-20 | Zonda Attila | https://cm.getmytestdomain.com/ | SIGN UP / Payment Methods | Card expiration shows 3 months total | The drop down shows only 3 months total | 1.Open Link 2.Click on Sign Up 3.Under payment methods interact with box Month click on dropdown | The user should be able to pick 1 out of 12 months total | Only 01, 02, 03 can be picked | Critical | Urgent | Open | Chrome 127 / Windows 11 | https://imgur.com/oJdR7Px
BUG-012 | 2026-08-20 | Zonda Attila | https://cm.getmytestdomain.com/ | SIGN UP / Payment Methods | Card year shows up to 2023 | The drop down shows up to 2023 only | 1.Open Link 2.Click on Sign Up 3.Under payment methods interact with box Year click on dropdown | The user should be able to pick years up to 2030 at least since we are in 2026 | Maximum year available is 2023 | High | High | Open | Chrome 127 / Windows 11 | https://imgur.com/VmE7Rfd
BUG-013 | 2026-08-21 | Zonda Attila | https://cm.getmytestdomain.com/ | SIGN UP / Payment Methods | CVV is not limited to 3 or 4 digits | Input field card security code digits are not limited to 3 or 4 digits only a warning message which says "CVV should be 3 or 4 digits" | 1.Open Link 2.Click on Sign Up 3.Under payment methods interact with box CVV 4.Type in more then 4 digits | The user should be limited to 3 4 digits maximum | The user should not be allowed to enter more then 3 / 4 digits total | Medium | Medium | Open | Chrome 127 / Windows 11 | https://imgur.com/xuD9KeY
BUG-014 | 2026-08-22 | Zonda Attila | https://cm.getmytestdomain.com/ | SIGN UP / Choose subscription plan | incorrect Text of "This membership fee permits one weak of access to the full website of testtitle.com" | The text should change based on the supbscription plan selected | 1.Open Link 2.Click on Sign Up 3.Under text Sign up for access to website 4.Click on each plan individualy | The user should see the correct txt based on their choice of subscription | The text does not change | Medium | Medium | Open | Chrome 127 / Windows 11 | https://imgur.com/EfWBGSB
BUG-015 | 2026-08-23 | Zonda Attila | https://cm.getmytestdomain.com/ | SIGN UP / Payment Information Banner | Text and background almos has same colors | text color style="color: rgb(227, 226, 226);" background: rgb(255, 255, 255) The two colors almost identical | 1.Open Link 2.Click on Sign Up 3.Check the information banner under the Signup section | The user should have a clean and easily readable text | The text is blurry not visible enough hard to distinguish for the human eye | Low | Medium | Open | Chrome 127 / Windows 11 | https://imgur.com/h3UzUVe
BUG-016 | 2026-08-24 | Zonda Attila | https://cm.getmytestdomain.com/ | Front page / Navigation bar | Navigation menu links incorrectly redirect to the homepage | Clicking navigation items such as Video Courses, Articles, or Contact redirects the user back to the homepage instead of the selected page. | 1.Open Link 3.Clicking navigation items such as Video Courses, Articles, or Contact | Each navigation link should open its corresponding page. | All navigation links redirect to the front/home page | High | Urgent | Open | Chrome 127 / Windows 11

## Summary
Bug Report Summary
Total Bugs | 17 | Severity | Count
Open | 17 | Critical | 2
In Progress | 0 | High | 4
Blocked | 0 | Medium | 4
Closed | 0 | Low | 7
Critical | 2
High | 4
Medium | 4
Low | 7